## PMIP Gantt
PMIP — Public Music Intelligence Platform ¦ Gantt Chart
Project Start | Target Finish | Tasks | Complete | In Progress | Overall Progress |  | Legend
2026-08-24 | 2027-01-24 | 26 | 4 | 1 | 16 |  | Complete |  | In Progress |  | Not Started
Phase | Task | Start | End | Status | % Complete | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
Planning & Requirements | Define PMIP concept, scope and intelligence objectives | 2026-08-24 | 2026-08-24 | Complete | 100 | bar: 2026-08-24
Data Acquisition | Search, evaluate and download public music datasets | 2026-08-24 | 2026-08-25 | Complete | 100 | bar: 2026-08-24
Environment & Version Control | Set up project structure, Python environment and GitHub | 2026-08-25 | 2026-08-26 | Complete | 100 | bar: 2026-08-24
Data Exploration | Explore all three datasets and test artist matching | 2026-08-25 | 2026-08-26 | Complete | 100 | bar: 2026-08-24
Data Cleaning | Clean listeners dataset | 2026-08-26 | 2026-08-29 | Complete | 10 | bar: 2026-08-24
Data Cleaning | Clean cross-platform release dataset | 2026-08-29 | 2026-09-03 | Not Started | 1 | bar: 2026-08-24 to 2026-08-31
Data Cleaning | Clean 5.4M-row charts dataset using chunks | 2026-09-03 | 2026-09-10 | Not Started | 0 | bar: 2026-08-31 to 2026-09-07
Data Preparation | Create processed datasets and quality checks | 2026-09-08 | 2026-09-13 | Not Started | 0 | bar: 2026-09-07
Data Integration | Design analytical schema and artist/track matching pipeline | 2026-09-12 | 2026-09-22 | Not Started | 0 | bar: 2026-09-07 to 2026-09-21
Data Integration | Build unified artist, track, market and platform tables | 2026-09-20 | 2026-09-29 | Not Started | 0 | bar: 2026-09-14 to 2026-09-28
EDA & Visualisation | Analyse trends, markets, releases and cross-platform relationships | 2026-09-28 | 2026-10-09 | Not Started | 0 | bar: 2026-09-28 to 2026-10-05
Feature Engineering | Create artist momentum, growth and release features | 2026-10-07 | 2026-10-18 | Not Started | 0 | bar: 2026-10-05 to 2026-10-12
ML — Artist Momentum | Build and evaluate artist momentum model | 2026-10-19 | 2026-10-30 | Not Started | 0 | bar: 2026-10-19 to 2026-10-26
ML — Forecasting | Forecast streams and chart movement | 2026-10-26 | 2026-11-06 | Not Started | 0 | bar: 2026-10-26 to 2026-11-02
ML — Anomaly Detection | Detect unusual performance spikes and drops | 2026-11-02 | 2026-11-12 | Not Started | 0 | bar: 2026-11-02 to 2026-11-09
ML — Geography | Build listener geography intelligence | 2026-11-09 | 2026-11-20 | Not Started | 0 | bar: 2026-11-09 to 2026-11-16
ML — Market Growth | Model market growth by country/region | 2026-11-16 | 2026-11-27 | Not Started | 0 | bar: 2026-11-16 to 2026-11-23
ML — Release Intelligence | Build release intelligence scoring/model | 2026-11-23 | 2026-12-04 | Not Started | 0 | bar: 2026-11-23 to 2026-11-30
ML Evaluation | Compare models, metrics and explainability | 2026-12-01 | 2026-12-08 | Not Started | 0 | bar: 2026-11-30 to 2026-12-07
Data Engineering Pipeline | Automate ingestion, cleaning, validation and transformation | 2026-12-05 | 2026-12-18 | Not Started | 0 | bar: 2026-11-30 to 2026-12-14
Database & API | Design database and build analytics/ML API | 2026-12-14 | 2026-12-30 | Not Started | 0 | bar: 2026-12-14 to 2026-12-28
Public Website | Build label, artist, release and news pages | 2026-12-21 | 2027-01-08 | Not Started | 0 | bar: 2026-12-21 to 2027-01-04
Analytics Dashboard | Build charts, maps and intelligence dashboards | 2026-12-28 | 2027-01-12 | Not Started | 0 | bar: 2026-12-28 to 2027-01-11
Integration & Testing | Connect UI, API, database and models; test core flows | 2027-01-08 | 2027-01-18 | Not Started | 0 | bar: 2027-01-04 to 2027-01-18
Deployment | Deploy PMIP production environment | 2027-01-15 | 2027-01-22 | Not Started | 0 | bar: 2027-01-11 to 2027-01-18
Documentation | Complete README, architecture, data dictionary and portfolio case study | 2027-01-10 | 2027-01-24 | Not Started | 0 | bar: 2027-01-04 to 2027-01-18

## Milestones
Milestone | Target Date | Status | % Complete | Deliverable | Notes
Requirements & scope locked | 2026-08-24 | Complete | 100 | PMIP requirements/specification
Datasets acquired | 2026-08-25 | Complete | 100 | 3 raw datasets stored locally
Data exploration complete | 2026-08-26 | Complete | 100 | 01_data_exploration.ipynb
GitHub repository established | 2026-08-26 | Complete | 100 | PMIP GitHub repository
Data cleaning complete | 2026-09-13 | In Progress | 10 | 02_data_cleaning.ipynb + processed data
Unified analytical dataset ready | 2026-09-29 | Not Started | 0 | Integrated analytical tables
EDA & feature engineering complete | 2026-10-18 | Not Started | 0 | EDA + model-ready features
All ML intelligence models evaluated | 2026-12-08 | Not Started | 0 | Model metrics and explainability
Automated data pipeline complete | 2026-12-18 | Not Started | 0 | Reusable pipeline
Backend/API complete | 2026-12-30 | Not Started | 0 | Database + API
Public website/dashboard complete | 2027-01-12 | Not Started | 0 | PMIP web application
Production deployment complete | 2027-01-22 | Not Started | 0 | Live PMIP deployment
Documentation complete | 2027-01-24 | Not Started | 0 | README + architecture + portfolio case study